## Sheet1
Red text is only an Example - To be amended as necessary throghout the table
Category | Name | Associated Deliverable | Associated Activity | Risk description & Details | Likelihood | Impact | Risk Level (Taken from the table) | Risk Owner | Mitigation - What you do to try to prevent the risk or reduce its likelihood/impact. | Contingency - What you will do if the risk actually happens.
Recruitment/Operational | Delayed participant recruitment | D2 – Participant recruitment and baseline data collection | A2.1 – Recruitment and enrolment of research participants | Recruitment may be slower than anticipated, resulting in an insufficient number of participants being enrolled within the planned timeframe. This could delay data collection and subsequent analysis activities and may affect the project timeline. | Likely | Significant | High | Principal Investigator | Begin recruitment early; monitor recruitment rates monthly; engage additional recruitment sites and relevant stakeholder groups; ensure recruitment materials and processes are ready before the activity begins. | If recruitment remains below target, extend the recruitment period, activate additional recruitment sites or participant sources, and revise the project timetable where necessary.